## Sheet1
Member | Position | Tasks - Modules To develop | Deliverables | Timetable |  |  | Estimated Hours of Work | Rate per hour | Estimated Cost
|  |  |  | 2021-04-05 | 2021-04-06 | 2021-04-07
Diego Bravo Torres | Team Lead and Developer | Conversions Tokenizing | converting.h converting.c tokenizing.h tokenizing.c main.c | Planning | Execution and testing | Delivering | 8 hours per day: 3 days x 8 hours = 24hrs | 31 CAD | 31 x 24 = 744
Woongyoung Kim | Senior Developer | Fundamentals | fundamentals.h fundamentals.c | Planning | Execution and testing | Delivering | 9 hours per day: 3 days x 8 hours = 24hrs | 30 CAD | 30 x 24 = 720
Zimo Han | Senior Developer | Manipulations | manipulating.h manipulating.c | Planning | Execution and testing | Delivering | 10 hours per day: 3 days x 8 hours = 24hrs | 30 CAD | 30 x 24 = 720
[8 empty] | Estimated Cost | 2184 CAD